# Probability/Impact Matrix

## 15 November 2021

**Project Name:** Global Treps Project

**Identified Risks:**

R1: Bad communication Impact score: 10

R2: Team Members in Different Countries Impact score: 10

R3: No LiveStream Version Impact score: 5

R4: Outsourcing Videos Impact score: 6

R5: Different Personalities Impact score: 4

R6: Ashok’s Injury Impact score: 7

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Probability | High |  |  | R1  R2 |
| Medium | R5 | R3  R4 |  |
| Low |  |  | R6 |
|  |  | Low | Medium | High |
|  | Impact | | | |